## Issues Log
ISSUES LOG
Project Name:
Project Manager
Issue # | Issue Category | Brief Description | Impact | Decision/Resolution | Priority (H,M, L) | Status (Open, Commenced, Closed) | Raised By | Assigned To | Response Date | Close Date
| e.g. Technical | e.g. Broken plotter is preventing engineers from publishing project drawings. | Causing delays to schedule | e.g. External supplier sourced. Submitted a help desk ticket (# 6051232) and the plotter was repaired and operational on 2/25/xx. | M | Commenced | J Smith | R White | 2018-02-24
| e.g. Sponsor Support/Approval | e.g. Lease for the new facility is in jeopardy of missing 5/1/18 cutoff date for approval. | Delays the schedule and resources ready to start on the work. | e.g. Escalated the issue with the VP of Facilities on 4/1/18. He indicated that he should obtain approval of the lease by 4/25/12. I will follow up twice a week until issue is resolved. | M | Commenced | T Tanks | R White | 2018-01-04
| e.g. Resource | e.g. Testing group director recently retired and has a new director. We must ensure support and resource allocation for the project. | Delays. Loss of expertise, Test team may not be available as expected. | e.g. J. Doe met with new testing group director on 4/3/19 and received formal support for the project and resources that have already been assigned by previous director. | M | Closed | J Doe | E Red | 2019-03-04 | 2019-03-07
| e.g. Data Integration | e.g. Unable to create a protocol to extract data from a legacy system, SWAN. | Delays. Need to invest time to explore other techniques and tools. |  | H | Open | R White | P Thomas | 2019-05-02

## Drop down list
Drop down list
| Issue Type | Priority | Status
| Benefit/Value shortfall | High | Open
| Budget | Medium | Closed
| Business Processes | Low | Commenced
Change Control
Compliance
Data Quality
Design
Facilities
Integration
Performance
Procurement Disputes
Quality of the Deliverables
Resistance to Change
Resource
Scope Creep
Skills
Sponsor Support/Approval
Supply
Technical
User Acceptance Testing
Other

## Guidance
What is an Issue?
A project issue is an event or condition that will have or has a negative impact on the project. The situation is recoverable or can be mitigated in some way. An issue is often a risk that has materialised. An issue is not a failure because a failure is in the past and cannot be managed. Some common project issues are:
Issue Categories
Benefit/Value shortfall
A business area begins to realise that a project is not going to be commercially successful or strategically valuable.
Budget
The cost of a service or product/material is higher than original anticipated and outside tolerance.
Business Processes
The business area points out later in the project that the new system is incompatible with critical business processes.
Change Control
A project is being pushed to accept more work without more budget and time.
Compliance
The product fails to comply with Australian laws, regulations or standards.
Data Quality
The data quality issue type can be duplicate data, data stored in the wrong category, incorrect data, incomplete data, not current data, merged data, lack of data dictionary, lack of data owner/custodian, does not meet compliance or security requirements, technical limitations to readily access the data, or other. NOTE - The Project Manager is required to inform the Data Governance Committee of any data quality issues raised.
Design
The software architecture relies on an unstable or inappropriate component.
Facilities
A facility is not ready or accessible at the agreed time.
Integration
A system part does not respond as per the specifications, causing integration testing to fail.
Performance
The supplier or team delivers work late and/or to a low quality.
Procurement Disputes
The supplier insists on payment before progressing the work.
Quality of the Deliverable
Deliverables are low quality causing delays or rejection of the deliverables
Resistance to Change
Some stakeholders want the project to fail and take action to block progress.
Resources
An expert on the project resigns in the middle of the project.
Scope creep
Requirements are broader than the approved scope of work.
Skills
The team does not have the skills expected at the start of the project and team members require training and time to come up to speed.
Sponsor Support/Approval
A key stakeholder is disengaged, untimely and/or unresponsive to requests to help clear roadblocks such as budget approvals.
Supply
A material required for a building project is not delivered on time.
Technical
Developers cannot find the root cause of a defect in the software/system. System/tool is broken/faulty.
User Acceptance testing
Testing fails due to major defects.
Other
As required by the project.
Schedule
A task or work package will take longer than expected and is outside tolerance
Operations
Production down time required, blackouts required, extended outages.
Legal
Data privacy breach or complaints from civilians about a construction project.
Testing
Testing misses a defect that goes into production and customers complain and there is a regulatory enquiries.
Information security
Prior to launch a data security vulnerability is discovered in the system.
Weather
Construction project is delayed due to an act of god.
Geology
Geological or archaeological formations were not discovered during planning surveys.
Note - You can create more categories as required for your project.