## Sheet1
Claims Management System Corrective Action Plan April 2020
An external audit of the workers compensation Claims Management System was conducted by Callida Consulting, on behalf of Comcare, from 16-20 March 2020. The following corrective action plan details actions to be undertaken in response to the observations identified. No non-conformances were identified.
Observations
Observation | Corrective Action | Action Officer | Date to be Completed | Status | Evidence
Element 3. Implementation
Criterion 3.3 The determining authority communicates relevant information regarding the claims management process.
The ANU should consider whether key decisions captured in the claims tracker should also be captured on the claim file. | Following each of the regular claims review meetings, a file note is to be created and placed on the individual claim file, for any claim discussed. | Claims Services Officers | Ongoing | Completed | Attachment A - Email to claims team
| Update the relevant procedure in the ANU Claims Manual to include the step of creating a file note following case discussions. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment B - Excerpt from Claims Manual (Claim Reviews)
| Discuss the new procedure at the next fortnightly Claims team meeting to ensure all claims staff are aware of the requirement to create a file note. | Lisa McLoughlin | 2020-04-17 | Completed | Attachment C - Team meeting invite
| Monitor the implementation and conformance with the new procedure through the internal audit of claims management as per the existing procedure. | Lisa McLoughlin | Ongoing | Completed | Attachment D - Internal Audit template
Criterion 3.5 The determining authority complies with the provisions of the SRC Act when making decisions on claims.
The ANU Template Letter 37: Section 30 and 137 Lump sum Redemption Payment, does not prompt the claims manager to record the reasons and does not include a notice of rights. | Update Template Letter 37 to include section for reasoning, and attached the notice of rights to the Template Letter. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment E - Letter Template 37
Criterion 3.7 The determining authority complies with the provisions of the SRC Act when determining initial liability.
The ANU should update the Claims Manual to cover sections 52, 55, and 117 of the SRC Act. | Update the ANU Claims Manual to include brief explanation of section 52 of the SRC Act. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment F - Excerpt from Claims Manual
| Update the ANU Claims Manual to include brief explanation of section 55 'survival of claims' of the SRC Act. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment G - Excerpt from Claims Manual
| Update the ANU Claims Manual to include brief explanation of section 117 'Locally Engaged Overseas Employees' of the SRC Act. | Lisa McLoughlin | 2020-05-31 | In Progress | Attachment H - Excerpt from Claims Manual
| Discuss at fortnightly Claims team meeting to ensure all claims staff are aware of these provisions. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment C - Team meeting invite
Criterion 3.9 The determining authority complies with the provisions of the SRC Act when determining liability for benefits, including medical expenses.
The ANU should update the Claims Manual to note section 108E(a) of the SRC Act requires licensees to make payments accurately and quickly, ensure that s16 determinations align with the Medical Certificate or treatment plan, explore options to reconcile payments with Finance records. | Update the Claims Manual to note section 108E(a) of the SRC Act requires licensees to make payments accurately and quickly, and define the University's expectations with regard to 'quickly'. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment I - Excerpt from Claims Manual - payment of invoices and receipts
| Discuss at fortnightly Claims team meeting to ensure all claims staff, where possible, align treatment approvals with medical certificates/treatment plans. | Lisa McLoughlin | 2020-04-17 | Completed | Attachment C - Team meeting invite
| Create and implement procedure to ensure audit of payments recorded in Figtree is undertaken and reconciled with payments issued by Finance. | Lisa McLoughlin | 2020-05-31 | In Progress | J
Criterion 3.14 Claim reviews are timely, made accuratelyand guided by equity, good conscience and the the substntial merits of each case without regards to technicalities.
The ANU should consider tailoring the QA form to ensure key components are considered. | Update the Email QA template to include sections to show what legislative provisions were checked, and for further detail of extent of the QA undertaken. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment K - QA template
Criterion 3.17 The determining authority maintains the relevant level of reporting, records and documentation to support its programs and legislative compliance
Claims Managers need to be more systemic in their recordkeeping processes to ensure documentation is captured in both Figtree and the shared drive claim file. | As per corrective action implemented in February 2020, use the Internal Audit Tool procedure to ensure CSO's have saved all correspondence to the Figtree file and the shared drive claim file. | Lisa McLoughlin | Ongoing | Completed | Attachment D - Internal Audit template
Criterion 4.5 The determining authority informs Comcare as soon as practicable of any proceedings in relation to a matter arising under the SRC Act.
The ANU may wish to consider updating the Claims Manual to include that notification of AAT matters must be made to Comcare as soon as practicable. | The CDW reporting undertaken monthly notifies Comcare of any new AAT matter. Comcare has previously confirmed that no additional notification is required. Update the Claims Manual to note this advice. | Lisa McLoughlin | 2020-05-31 | Completed | Attachment L - Excerpt from Claims Manual - AAT applications